## Sheet1
| Unmitigated Risk | [5 empty] | Actions
| ID | Risk Description | Likelihood | Impact | Severity | Owner | Mitigation Actions
Design Risks | 1 | Not completing tasks at deadlines | Possible | Moderate | Medium | Team | Drafted Gantt Chart to montior task and ensure that all team members were scheduled to complete tasks. Schedule reviews in between mentor sessions to re-align team
| 2 | Team member overload | Possible | Significant | Medium High | Team | Ensure that mutliple people are assigned to each task. Record misunderstandings in the group document to ask each other and the mentor where applicable
| 3 | Miscommunications | Unlikely | Moderate | Low Medium | Team | Reviews in between mentor sessions to re-align team. Use of chat to ensure all team members are able to raise and assist each other
| 4 | Emergent Tasks | Possible | Significant | Medium High | Team | Unplanned tasks that arise shall be raised in the team chat. The team shall re-evaluate current personel distribution and re-allocate as necessary. Modifications to the team member and timeline shall be agreed by all members.
| 5 | Losing Team Members | Very Unlikely | Severe | Medium | Team | All team members shall be familiar with the whole design. Team members shall avoid working alone and communicate often about progress.
Product Risks | 6 | SPICE Model inaccuracies | Likely | Significant | Medium High | D1, D3 | Refer to datasheets where applicable. Understand the simplifications of the SPICE model, especially active components. Perform monte-carlo and tolerance analysis.
| 7 | Product Failure (Electrical) | Likely | Severe | High | D4 | Protetction on high current circuits. Failsafe design where potential sources of power can be eliminated safely.
| 8 | Product Failure Performance | Unlikely | Significant | Medium | D1, D3, D4 | Key metrics shall be over designed in the models. Perform monte-carlo and tolerance analysis.
| 9 | Product Failure Translation | Unlikely | Significant | Medium | D1, D2, D4 | Use a large sample of test cases in simulation. Ensure modelled noise is realistic. Build a metric of the translation accuracy in the test environment
| 10 | Model Failure (Presnetation) | Very Likely | Negligible | Low Medium | Team | Before the presentation, ensure that all metrics have been documented with images in the event of a failure.

## Sheet2
Risk Matrix
| Negligible | Minor | Moderate | Significant | Severe
Very Likely | Low Med | Medium | Med Hi | High | High
Likely | Low | Low Med | Medium | Med Hi | High
Possible | Low | Low Med | Medium | Med Hi | Med Hi
Unlikely | Low | Low Med | Low Med | Medium | Med Hi
Very Unlikely | Low | Low | Low Med | Medium | Medium